## W1
PROJECT REPORT
Group | Group 4
Week | 09/05/2022-15/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Context diagram | In Progress | Describes the product's context in the form of a context diagram in which you present the boundary and connections between the system you’re developing and everything else in the universe.
2 | Write introduction | In Progress | Presents a high-level overview of the product and the environment in which it will be used, the users, and known constraints, assumptions, and dependencies.
3 | Screen flow | In Progress | Shows the system screens and the relationship among screens.
4 | Screen Details | Pending | Provide the descriptions for the screens in the Screens Flow.
5 | User Authorization | Pending | Provide the system roles authorization to the system features.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Draw Context diagram | PhongNT | Draw data flow of objects interacting with the system.
2 | Write introduction | QuyenPTT | Write detailed description of the circumstances that created the Academic Blog at FPTU.
3 | Screen flow | TamNT | Select the necessary screens for the project and draw the relationships between them.
4 | Screen Details | LocNQ | Select the appropriate features for each screen, describe specifically the functions and interfaces of the features.
5 | User Authorization | ThanhHT | Select which users are allowed to access the screens and list the specific functions of each screen.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | There are not too many ideas to write the introduction of the project. | In Progress | Read some more documents.
2 | There is no difference between the roles in the context diagram. | In Progress | Edit data flow of student and mentor/ lecturer.
3 | Having difficulty deploying the screens in a logical and easy-to-see way. | In Progress | Redesign the screen flow to be more reasonable and logical.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Non-Screen Functions | 17/05/2022 | Provide the descriptions for the non-screen system functions, i.e batch/cron job, service, API, etc.
2 | Continue write Screen Details | 19/05/2022 | Update missing screens and features to the plan.
3 | Continue write User Authorization | 19/05/2022 | Update user access and functions to the plan.
4 | Common Requirements | 20/05/2022 | List possible common requirements and provide specific descriptions of them.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
N/A
Note on A1: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue -Author ---- Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed -Author
Note on C5: ====== ID#AAAAZoRZnec Author (2022-05-22 14:44:43) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C21: ====== ID#AAAAZoRZneg Author (2022-05-22 14:44:43) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W2
PROJECT REPORT
Group | Group 4
Week | 16/05/2022-22/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Screen Flow | Completed | Shows the system screens and the relationship among screens.
2 | Scren Details | Completed | Provide the descriptions for the screens in the Screens Flow.
3 | User Authorization | Completed | Provide the system roles authorization to the system features.
4 | Non-Screen Functions | Completed | Provide the descriptions for the non-screen system functions, i.e batch/cron job, service, API, etc.
5 | Common Requirements | Completed | List possible common requirements and provide specific descriptions of them.
6 | Entity Relationship Diagram | In Progress | Draw the entities that exist in the system, their attributes and relationships among them.
7 | Product Backlog | Completed | List the functions that need to be executed in the system and prioritize the most important functions that will be at the top of this backlog.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design Screen Flow | PhongNT | Edit the screen flow to be reasonable and logical.
2 | Write Scren Details | ThanhHT | List specific screens and features in the document.
3 | Write User Authorization | All | List user access and function in the document.
4 | Write Non-Screen Functions | QuyenPTT | List possible the non-screen system functions and provide specific descriptions of them.
5 | Write Common Requirements | TamNT | List common requirements and provide descriptions.
6 | Design Entity Relationship Diagram | LocNQ | Draw the entities, identify the attributes and relationships of each entity.
7 | Write Product Backlog | All | Consider and sort the functions in priority order.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Having difficulty listing all the functions in each feature. | Completed | Review results in multiple times to avoid duplication of functions.
2 | Difficulty in identifying and completeness of entities during ERD design. | In Progress | Refer to mentor's feedback and edesign ERD to be more reasonable and logical.
3 | Difficulty in designing web pages. | In Progress | Refer to more templates.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete Entity Relationship Diagram | N/A | Complete the ERD.
2 | Create Database | N/A | Create a database based on existing ERD.
3 | Sign in with Google | N/A | Implement Sign in with Google function.
4 | Search blogs by name | N/A | Implement Search blogs by name function.
5 | Search blogs by major | N/A | Implement Search blogs by major function.
6 | View list Blogs | N/A | Implement View list Blogs function.
7 | View personal page | N/A | Implement View personal page function.
8 | Post blog | N/A | Implement Post blog function.
9 | Edit blog | N/A | Implement Edit blog function.
10 | Delete blog | N/A | Implement Delete blog function.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Design Web pages by Figma | TamNT | Maybe it will be difficult because it is the first time that all members use it.
2 | Use online tool to design ERD | QuyenPTT | Because ERD will be more beautiful and easier to see than hand-crafted design.
Note on C5: ====== ID#AAAAZne8KA8 Author (2022-05-22 14:46:38) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C26: ====== ID#AAAAZne8KBA Author (2022-05-22 14:46:38) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W3
PROJECT REPORT
Group | Group 4
Week | 23/05/2022-29/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Update Screen Flow | Completed | Add some missing pages in screen flow.
2 | Update Screen Details | Completed | Provide more pages along with page detail editing
3 | Update User Authorization | Completed | Add some access to additional pages for users.
4 | Update Non-Screen Functions | Completed | Change some unreasonable details.
5 | Update Common Requirements | In Progress | Need to add some details.
6 | Entity Relationship Diagram | In Progress | Draw the entities that exist in the system, their attributes and relationships among them.
7 | Update Product Backlog | Completed | Add more the functions that need to be executed in the system.
8 | Draw wireframes | In Progress | Design several screens and demonstrate some basic functions on them
9 | Update Context Diagram | Completed | Describe the system's flows in detail and add flows from "Mentor" to the system
10 | Create Code Packages | Completed | Design with some necessary code packages.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Update Screen Flow | LocNQ | Change the "mentors page" screen to the "mentor blog list" screen. Add "Mentor registration" screen to the screen flow.
2 | Update Screen Details | ThanhHT | Add some descriptions for new screens.
3 | Update User Authorization | All | Add some access to new pages for users.
4 | Update Non-Screen Functions | QuyenPTT | Edit some unreasonable details.
5 | Update Common Requirements | TamNT | Add more common requirements.
6 | Design Entity Relationship Diagram | ALL | Adjust some of the relationships between entities adding some attributes to those entities
7 | Update Product Backlog | PhongNT | Add more new functions and sort the functions in priority order.
8 | Draw wireframes | QuyenPTT | Design some necessary screens that are suitable for the project.
9 | Update Context Diagram | LocNQ | Edit and add some flows to the diagram.
10 | Create Code Packages | ThanhHT | Create code packages with some basic packages.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Difficulty expressing relationships between entities in ERD design | In Progress | The relationships between entities to find the metor with the appropriate subject to approve the blog post are not correct and logical.
2 | There are no more ideas for designing wireframes. | In Progress | Refer to more templates.
3 | Each member has different opinions on ERD design. | Completed | Select the most approved opinion.
4 | Difficulty to define roles between users. | Completed | Redefine the functions of each role again.
5 | Not fully designed wireframes (functional screens). | In Progress | Reference and design more.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete Entity Relationship Diagram | N/A | Complete the ERD.
2 | Create Database | N/A | Create a database based on existing ERD.
3 | Sign in with Google | N/A | Implement Sign in with Google function.
4 | Search blogs by subject | N/A | Implement Search blogs by subject function.
5 | Search blogs by major | N/A | Implement Search blogs by major function.
6 | View list Blogs | N/A | Implement View list Blogs function.
7 | View personal page | N/A | Implement View personal page function.
8 | Post blog | N/A | Implement Post blog function.
9 | Edit blog | N/A | Implement Edit blog function.
10 | Delete blog | N/A | Implement Delete blog function.
11 | Design welcome page | N/A | Design the first page of the system.
12 | Fully design wireframes (functional screens). | N/A | Design functional screens.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | It is proposed to merge admins and students into users in the ERD. | TamNT | Because ERD will be more difficult to design if two roles are differ.
2 | Merge 2 entities "Mentor" and "Student" in ERD into user | TamNT | Because the properties of these two entities are quite similar, it is possible to combine the two entities and process the other properties using decentralized authentication.
3 | Students can register as Mentor | VanVTT10 | Because of students can provide certificates to prove their qualifications, they can be mentors for that subject
Note on C5: ====== ID#AAAAZne8KA8 Author (2022-05-22 14:46:38) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C32: ====== ID#AAAAZne8KBA Author (2022-05-22 14:46:38) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue