## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
No | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
1 | Login with Google | Welcome | Simple | Iteration 1 | SE150351 | Phan Thị Tố Quyên
2 | Post blog | Write blog | Simple | Iteration 1 | SE150412 | Hồ Tấn Thành
3 | View blog list | View blog | Simple | Iteration 1 | SE150338 | Nguyễn Quốc Lộc
4 | Edit blog | View blog | Simple | Iteration 1 | SE150421 | Nguyễn Thành Tâm
5 | Delete blog | View blog | Simple | Iteration 1 | SE150407 | Nguyễn Thái Phong
6 | Search blog by major | Home page | Simple | Iteration 1 | SE150407 | Nguyễn Thái Phong
7 | Search blog by subject | Home page | Simple | Iteration 1 | SE150412 | Hồ Tấn Thành
8 | Search blog by title | Home page | Simple | Iteration 1 | SE150338 | Nguyễn Quốc Lộc
9 | Sort blog by vote | Home page | Simple | Iteration 1 | SE150421 | Nguyễn Thành Tâm
10 | Sort blog by date | Home page | Simple | Iteration 1 | SE150351 | Phan Thị Tố Quyên
11 | Vote blog | View blog | Simple | Iteration 1 | SE150407 | Nguyễn Thái Phong
12 | View number of vote | View blog | Simple | Iteration 1 | SE150412 | Hồ Tấn Thành
13 | View blog detail | View blog | Simple | Iteration 1 | SE150338 | Nguyễn Quốc Lộc
14 | Comment | View blog | Simple | Iteration 1 | SE150421 | Nguyễn Thành Tâm
15 | Give feedback about system | Give feedback | Simple | Iteration 1 | SE150351 | Phan Thị Tố Quyên
16 | Give feedback about Mentor | Give feedback | Simple | Iteration 1 | SE150407 | Nguyễn Thái Phong
17 | View draft blog | Manage draft blog | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành
18 | Delete draft blog | Manage draft blog | Simple | Iteration 2 | SE150338 | Nguyễn Quốc Lộc
19 | Mentor register | Mentor register | Simple | Iteration 2 | SE150421 | Nguyễn Thành Tâm
20 | View profile | Manage profile | Simple | Iteration 2 | SE150351 | Phan Thị Tố Quyên
21 | view personal page | Manage profile | Simple | Iteration 2 | SE150407 | Nguyễn Thái Phong
22 | Edit profile | Manage profile | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành
23 | View history activity list | Manage activity | Simple | Iteration 2 | SE150338 | Nguyễn Quốc Lộc
24 | View history activity detail | Manage activity | Simple | Iteration 2 | SE150421 | Nguyễn Thành Tâm
25 | Delete activity | Manage activity | Simple | Iteration 2 | SE150351 | Phan Thị Tố Quyên
26 | Search activity | Manage activity | Simple | Iteration 2 | SE150407 | Nguyễn Thái Phong
27 | Logout | Home page | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành
28 | Approve blog | Approve blog | Simple | Iteration 2 | SE150338 | Nguyễn Quốc Lộc
29 | View approve blog list | Approve blog | Simple | Iteration 2 | SE150421 | Nguyễn Thành Tâm
30 | View approve blog detail | Approve blog | Simple | Iteration 2 | SE150351 | Phan Thị Tố Quyên
31 | View vote list | Vote rating | Simple | Iteration 2 | SE150407 | Nguyễn Thái Phong
32 | Sort vote | Vote rating | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành
33 | Give award | Vote rating | Simple | Iteration 2 | SE150338 | Nguyễn Quốc Lộc
34 | Ban account | Manage account | Simple | Iteration 2 | SE150421 | Nguyễn Thành Tâm
35 | Unban account | Manage account | Simple | Iteration 2 | SE150351 | Phan Thị Tố Quyên
36 | View user activities | User details | Simple | Iteration 2 | SE150407 | Nguyễn Thái Phong
37 | View account list | Manage account | Simple | Iteration 2 | SE150412 | Hồ Tấn Thành
38 | Accept user request (hay là censor user requests ) | Mentor register | Simple | Iteration 3 | SE150338 | Nguyễn Quốc Lộc
39 | View feedback list | Feedback List | Simple | Iteration 3 | SE150421 | Nguyễn Thành Tâm
40 | View feedback detail | Feedback details | Simple | Iteration 3 | SE150351 | Phan Thị Tố Quyên
41 | Search feedback | Feedback List | Simple | Iteration 3 | SE150407 | Nguyễn Thái Phong
42 | Create major | Manage major | Simple | Iteration 3 | SE150412 | Hồ Tấn Thành
43 | View major list | Manage major | Simple | Iteration 3 | SE150338 | Nguyễn Quốc Lộc
44 | Edit major | Manage major | Simple | Iteration 3 | SE150421 | Nguyễn Thành Tâm
45 | Delete major | Manage major | Simple | Iteration 3 | SE150351 | Phan Thị Tố Quyên
46 | Search major | Manage major | Simple | Iteration 3 | SE150407 | Nguyễn Thái Phong
47 | Create subject | Manage subject | Simple | Iteration 3 | SE150412 | Hồ Tấn Thành
48 | View subject list | Manage subject | Simple | Iteration 3 | SE150338 | Nguyễn Quốc Lộc
49 | Edit subject | Manage subject | Simple | Iteration 3 | SE150421 | Nguyễn Thành Tâm
50 | Delete subject | Manage subject | Simple | Iteration 3 | SE150351 | Phan Thị Tố Quyên
51 | Search subject | Manage subject | Simple | Iteration 3 | SE150407 | Nguyễn Thái Phong
52 | Logout | Admin page | Simple | Iteration 3 | SE150412 | Hồ Tấn Thành