## Wx
PROJECT REPORT
Group | <Group 4>
Week | 16/05/2022-22/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Screen Flow | Completed | Shows the system screens and the relationship among screens.
2 | Scren Details | Completed | Provide the descriptions for the screens in the Screens Flow.
3 | User Authorization | Completed | Provide the system roles authorization to the system features.
4 | Non-Screen Functions | Completed | Provide the descriptions for the non-screen system functions, i.e batch/cron job, service, API, etc.
5 | Common Requirements | Completed | List possible common requirements and provide specific descriptions of them.
6 | Entity Relationship Diagram | In Progress | Draw the entities that exist in the system, their attributes and relationships among them.
7 | Product Backlog | Completed | List the functions that need to be executed in the system and prioritize the most important functions that will be at the top of this backlog.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design Screen Flow | PhongNT | Edit the screen flow to be reasonable and logical.
2 | Write Scren Details | ThanhHT | List specific screens and features in the document.
3 | Write User Authorization | All | List user access and function in the document.
4 | Write Non-Screen Functions | QuyenPTT | List possible the non-screen system functions and provide specific descriptions of them.
5 | Write Common Requirements | TamNT | List common requirements and provide descriptions.
6 | Design Entity Relationship Diagram | LocNQ | Draw the entities, identify the attributes and relationships of each entity.
7 | Write Product Backlog | All | Consider and sort the functions in priority order.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Having difficulty listing all the functions in each feature. | Completed | Review results in multiple times to avoid duplication of functions.
2 | Difficulty in identifying and completeness of entities during ERD design. | In Progress | Refer to mentor's feedback and edesign ERD to be more reasonable and logical.
3 | Difficulty in designing web pages. | In Progress | Refer to more templates.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete Entity Relationship Diagram | 24/05/2022 | Complete the ERD.
2 | Create Database | 25/05/2022 | Create a database based on existing ERD.
3 | Sign in with Google | 26/05/2022 | Implement Sign in with Google function.
4 | Search blogs by name | 26/05/2022 | Implement Search blogs by name function.
5 | Search blogs by major | 26/05/2022 | Implement Search blogs by major function.
6 | View list Blogs | 27/05/2022 | Implement View list Blogs function.
7 | View personal page | 27/05/2022 | Implement View personal page function.
8 | Post blog | 28/05/2022 | Implement Post blog function.
9 | Edit blog | 29/05/2022 | Implement Edit blog function.
10 | Delete blog | 29/05/2022 | Implement Delete blog function.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Design Web pages by Figma | TamNT | Maybe it will be difficult because it is the first time that all members use it.
2 | Use online tool to design ERD | QuyenPTT | Because ERD will be more beautiful and easier to see than hand-crafted design.